## 📊 Dashboard
Implementation Tracker Dashboard
All data pulled live from Customers, Milestones & Action Items sheets ¦ Built by Amitesh Anirudhan
Total Customers |  | Active Implementations |  | Avg. Progress |  | Overdue Actions
4 |  | 100 |  | 50.89% |  | 0
CUSTOMER OVERVIEW — Live from all sheets
Customer | Stage | Go-Live | Milestones Done | Actions Open | Overall % | CSM Owner
Sunrise Senior Living | Configuration | 2025-08-15 | 2 / 7 | 2 | 28.57% | Amitesh A.
Brightview Communities | Data Migration | 2025-09-01 | 2 / 4 | 2 | 50% | Amitesh A.
Atria Senior Living | Training | 2025-07-30 | 3 / 4 | 1 | 75% | Amitesh A.
Brookdale Senior | Discovery | 2025-10-01 | 1 / 2 | 1 | 50% | Amitesh A.

## 🗂 Customers
CUSTOMER REGISTRY - Master List (all other sheets pull from here)
Customer Name | Contract Start | Go-Live Target | Implementation Type | Stage | CSM Owner | Tech Contact | Notes
Sunrise Senior Living | 2025-03-01 | 2025-08-15 | Full Implementation | Configuration | Amitesh A. | John Smith | On track
Brightview Communities | 2025-03-15 | 2025-09-01 | Full Implementation | Data Migration | Amitesh A. | Sarah Lee | Data delay
Atria Senior Living | 2025-02-01 | 2025-07-30 | Full Implementation | Training | Amitesh A. | Mike Brown | Training May
Brookdale Senior | 2025-04-01 | 2025-10-01 | Integration Only | Discovery | Amitesh A. | Emily Davis | Kickoff done

## 🏁 Milestones
IMPLEMENTATION MILESTONES - Add customer name (dropdown from Customers sheet)
Customer | Milestone | Phase | Due Date | Completed | Status | Owner | Notes
Sunrise Senior Living | Kickoff Call | Discovery | 2025-03-05 | 2025-03-05 | Complete | Amitesh A. | All attended
Sunrise Senior Living | Requirements Sign-off | Discovery | 2025-03-15 | 2025-03-16 | Complete | Amitesh A. | Signed by COO
Sunrise Senior Living | System Configuration | Configuration | 2025-04-30 |  | In Progress | Amitesh A. | 75% done
Sunrise Senior Living | Data Migration | Data Migration | 2025-05-31 |  | Not Started | Amitesh A. | Awaiting data
Sunrise Senior Living | Training | Training | 2025-07-15 |  | Not Started | Amitesh A.
Sunrise Senior Living | UAT Sign-off | UAT | 2025-08-01 |  | Not Started | Amitesh A.
Sunrise Senior Living | Go-Live | Go-Live | 2025-08-15 |  | Not Started | Amitesh A.
Brightview Communities | Kickoff Call | Discovery | 2025-03-20 | 2025-03-20 | Complete | Amitesh A.
Brightview Communities | Requirements Sign-off | Discovery | 2025-04-01 | 2025-04-03 | Complete | Amitesh A. | Minor delays
Brightview Communities | Data Export | Data Migration | 2025-04-20 |  | Blocked | Amitesh A. | IT delay
Brightview Communities | Data Migration | Data Migration | 2025-05-15 |  | Not Started | Amitesh A. | Blocked
Atria Senior Living | Kickoff Call | Discovery | 2025-02-05 | 2025-02-05 | Complete | Amitesh A.
Atria Senior Living | Configuration | Configuration | 2025-03-01 | 2025-03-02 | Complete | Amitesh A.
Atria Senior Living | Data Migration | Data Migration | 2025-03-31 | 2025-04-01 | Complete | Amitesh A.
Atria Senior Living | Training Prep | Training | 2025-05-01 |  | In Progress | Amitesh A. | Deck 50% done
Brookdale Senior | Kickoff Call | Discovery | 2025-04-05 | 2025-04-05 | Complete | Amitesh A.
Brookdale Senior | Requirements | Discovery | 2025-04-20 |  | In Progress | Amitesh A.

## ✅ Action Items
ACTION ITEMS - Customer dropdown pulls from Customers sheet. Overdue rows highlight red.
Customer | Action Item | Owner | Due Date | Status | Priority | Notes
Sunrise Senior Living | Complete EHR field mapping document | Amitesh A. | 2025-04-25 | In Progress | 🔴 High | Send to client
Sunrise Senior Living | Schedule config review call | Amitesh A. | 2025-04-22 | Open | 🟡 Medium
Brightview Communities | Follow up on data export timeline | Amitesh A. | 2025-04-20 | Open | 🔴 High | Escalate if no reply
Brightview Communities | Send data migration template | Amitesh A. | 2025-04-24 | Open | 🟡 Medium
Atria Senior Living | Confirm training attendee list | Amitesh A. | 2025-04-23 | Complete | 🟢 Low | 12 confirmed
Atria Senior Living | Prepare training materials | Amitesh A. | 2025-05-01 | In Progress | 🟡 Medium | 50% done
Brookdale Senior | Send integration spec document | Amitesh A. | 2025-04-21 | Open | 🔴 High | Blocking go-live

## 📈 Progress
PROGRESS TRACKER - Auto-calculated from 🏁 Milestones sheet via COUNTIFS
Customer names pulled from 🗂 Customers sheet. Progress = Complete milestones / Total milestones per phase.
Customer | Discovery | Configuration | Data Migration | Training | UAT | Go-Live | Overall %
Sunrise Senior Living | 100% | 0% | 0% | 0% | 0% | 0% | 28.57%
Brightview Communities | 100% |  | 0% |  |  |  | 50%
Atria Senior Living | 100% | 100% | 100% | 0% |  |  | 75%
Brookdale Senior | 50% | [5 empty] | 50%

## 📖 How To Use
How To Use Implementation Tracker
Built by Amitesh Anirudhan ¦ github.com/amitesh0109 ¦ All sheets are connected via VLOOKUP/COUNTIFS
DATA FLOW — How sheets connect
🗂 Customers is the master | Add all customers here first. Every other sheet pulls customer names from this sheet automatically.
🏁 Milestones feeds Progress | The 📈 Progress sheet uses COUNTIFS on Milestones to calculate phase completion % per customer automatically.
✅ Action Items feeds Dashboard | Open action count per customer on the Dashboard is a live COUNTIFS from the Action Items sheet.
📊 Dashboard is read-only | Do not edit the Dashboard directly it pulls everything live from the other sheets.
HOW TO ADD A NEW CUSTOMER
Step 1 - Customers sheet | Add a new row in 🗂 Customers with name, dates, stage, and owner.
Step 2 - Milestones sheet | Add milestone rows. Select the customer name from the dropdown (it pulls from Customers automatically).
Step 3 - Action Items | Add action items. Select the customer from the dropdown.
Step 4 - Progress sheet | Add a new row. The customer name formula and all COUNTIFS update automatically.
Step 5 - Dashboard | Add a new row referencing the new Customers row. All KPIs update automatically.
TIPS
Overdue actions | Any action past its due date that is not Complete highlights red automatically.
Progress % | Calculated as Complete milestones / total milestones per phase using COUNTIFS on the Milestones sheet.
Dropdowns | Customer name, Stage, Status, and Priority fields all have dropdown validation.
Color scale | Progress sheet uses a red→amber→green color scale based on % complete per phase.