## 📊 Dashboard
Implementation Tracker Dashboard
Add customers in 🗂 Customers Dashboard updates automatically ¦ Works in Excel & Google Sheets
Total Customers |  | Active Implementations |  | Avg. Progress |  | Overdue Actions
4 |  | 20 |  | 50.89% |  | 0
CUSTOMER OVERVIEW Pre-populated formulas. Blank rows appear when customers are added.
Customer | Stage | Go-Live | Milestones Done | Actions Open | Overall % | CSM Owner
Sunrise Senior Living | Configuration | 2025-08-15 | 2 / 7 | 2 | 28.57% | Amitesh A.
Brightview Communities | Data Migration | 2025-09-01 | 2 / 4 | 2 | 50% | Amitesh A.
Atria Senior Living | Training | 2025-07-30 | 3 / 4 | 1 | 75% | Amitesh A.
Brookdale Senior | Discovery | 2025-10-01 | 1 / 2 | 1 | 50% | Amitesh A.

## 🗂 Customers
CUSTOMER REGISTRY - Master list. Add customers here. All other sheets update automatically.
Customer Name | Contract Start | Go-Live Target | Implementation Type | Stage | CSM Owner | Tech Contact | Notes
Sunrise Senior Living | 2025-03-01 | 2025-08-15 | Full Implementation | Configuration | Amitesh A. | John Smith | On track
Brightview Communities | 2025-03-15 | 2025-09-01 | Full Implementation | Data Migration | Amitesh A. | Sarah Lee | Data delay
Atria Senior Living | 2025-02-01 | 2025-07-30 | Full Implementation | Training | Amitesh A. | Mike Brown | Training May
Brookdale Senior | 2025-04-01 | 2025-10-01 | Integration Only | Discovery | Amitesh A. | Emily Davis | Kickoff done

## 🏁 Milestones
IMPLEMENTATION MILESTONES - Select customer from dropdown (auto-pulls from Customers sheet)
Update Status column as work progresses - Progress sheet recalculates automatically
Customer | Milestone | Phase | Due Date | Completed | Status | Owner | Notes
Sunrise Senior Living | Kickoff Call | Discovery | 2025-03-05 | 2025-03-05 | Complete | Amitesh A. | All attended
Sunrise Senior Living | Requirements Sign-off | Discovery | 2025-03-15 | 2025-03-16 | Complete | Amitesh A. | Signed by COO
Sunrise Senior Living | System Configuration | Configuration | 2025-04-30 |  | In Progress | Amitesh A. | 75% done
Sunrise Senior Living | Data Migration | Data Migration | 2025-05-31 |  | Not Started | Amitesh A. | Awaiting data
Sunrise Senior Living | Training | Training | 2025-07-15 |  | Not Started | Amitesh A.
Sunrise Senior Living | UAT Sign-off | UAT | 2025-08-01 |  | Not Started | Amitesh A.
Sunrise Senior Living | Go-Live | Go-Live | 2025-08-15 |  | Not Started | Amitesh A.
Brightview Communities | Kickoff Call | Discovery | 2025-03-20 | 2025-03-20 | Complete | Amitesh A.
Brightview Communities | Requirements Sign-off | Discovery | 2025-04-01 | 2025-04-03 | Complete | Amitesh A. | Minor delays
Brightview Communities | Data Export | Data Migration | 2025-04-20 |  | Blocked | Amitesh A. | IT delay
Brightview Communities | Data Migration | Data Migration | 2025-05-15 |  | Not Started | Amitesh A. | Blocked
Atria Senior Living | Kickoff Call | Discovery | 2025-02-05 | 2025-02-05 | Complete | Amitesh A.
Atria Senior Living | Configuration | Configuration | 2025-03-01 | 2025-03-02 | Complete | Amitesh A.
Atria Senior Living | Data Migration | Data Migration | 2025-03-31 | 2025-04-01 | Complete | Amitesh A.
Atria Senior Living | Training Prep | Training | 2025-05-01 |  | In Progress | Amitesh A. | Deck 50% done
Brookdale Senior | Kickoff Call | Discovery | 2025-04-05 | 2025-04-05 | Complete | Amitesh A.
Brookdale Senior | Requirements | Discovery | 2025-04-20 |  | In Progress | Amitesh A.

## ✅ Action Items
ACTION ITEMS - Customer dropdown pulls from Customers sheet automatically
Overdue items (past due date + not Complete) highlight red automatically
Customer | Action Item | Owner | Due Date | Status | Priority | Notes
Sunrise Senior Living | Complete EHR field mapping document | Amitesh A. | 2025-04-25 | In Progress | High | Send to client
Sunrise Senior Living | Schedule config review call | Amitesh A. | 2025-04-22 | Open | Medium
Brightview Communities | Follow up on data export timeline | Amitesh A. | 2025-04-20 | Open | High | Escalate if no reply
Brightview Communities | Send data migration template | Amitesh A. | 2025-04-24 | Open | Medium
Atria Senior Living | Confirm training attendee list | Amitesh A. | 2025-04-23 | Complete | Low | 12 confirmed
Atria Senior Living | Prepare training materials | Amitesh A. | 2025-05-01 | In Progress | Medium | 50% done
Brookdale Senior | Send integration spec document | Amitesh A. | 2025-04-21 | Open | High | Blocking go-live

## 📈 Progress
PROGRESS TRACKER Auto-calculated from Milestones. Pre-populated for all customers.
Blank rows show empty until a customer is added in 🗂 Customers
Customer | Discovery | Configuration | Data Migration | Training | UAT | Go-Live | Overall %
Sunrise Senior Living | 100% | 0% | 0% | 0% | 0% | 0% | 28.57%
Brightview Communities | 100% | - | 0% | - | - | - | 50%
Atria Senior Living | 100% | 100% | 100% | 0% | - | - | 75%
Brookdale Senior | 50% | - | - | - | - | - | 50%

## 📖 How To Use
How To Use Implementation Tracker
github.com/amitesh0109/saas-implementation-tracker ¦ Works in Excel & Google Sheets
HOW IT WORKS
Single source of truth | Add customers in 🗂 Customers. All other sheets pull from there no manual updates needed anywhere else.
Pre-populated formulas | Dashboard, Progress, and all formula columns are pre-filled for 20 customers. Blank rows stay hidden until a customer is added.
Works in Excel & Google Sheets | No QUERY functions used all VLOOKUP, COUNTIFS, and IF formulas work identically in both.
ADDING A NEW CUSTOMER
Step 1 - Customers | Add customer name, dates, stage, and owner in 🗂 Customers.
Step 2 - Milestones | Add milestones in 🏁 Milestones. Select customer from the dropdown.
Step 3 - Action Items | Add action items in ✅ Action Items. Select customer from the dropdown.
Step 4 - Done | Dashboard and Progress update automatically. No other steps needed.
TIPS
Overdue alerts | Action items past their due date that are not Complete highlight red automatically.
Progress % | Calculated as Complete milestones / total milestones per phase. Updates when you change status in Milestones.
Blank rows | Empty customer slots show blank on Dashboard and Progress they fill in automatically when you add a customer.
Max customers | Pre-populated for 20 customers. To add more, copy formulas down in Dashboard and Progress sheets.